## Urgent
Date | Task | Responsible | Due Date | Status | Comments
2014-02-25 | Finalise the design of the speaker | Senthil |  | Open | Bob is waiting for the PCB from the supplier and will send to Senthill
2014-02-25 | Design the new packaging changes + vac form and send to Josa | Scott | 28/02/2014 | Open
2014-02-25 | Solve the off centre problem with the speaker within 2 days. | Bob | 27/02/2014 | Open
2014-02-25 | Test this problem with speaker case vibration as RasPi is not very powerful. | Senthil |  | Closed | By limiting the speaker base, the vibration issue can be solved.
2014-02-25 | Make ID for each component (Description on BOM) work with MAP | JingJing |  | Open
2014-02-25 | Chase up with Bob about SD cards in the meeting tmr, need to make sure it is the best quality | JingJing |  | closed
27/02/2014 | DFM reviewed and drawings need to be modified | Andrew Liu/Scott | 2014-02-03 | open
28/02/2014 | complete the part in Red in the project chart | Jingjing | 2014-04-03 | open
2014-03-03 | Verify China trip details and finalise agenda | Yonatan | 2014-12-03 | open
2014-03-03 | Follow up with CP on compliance of the case | Jingjing | 2014-07-03 | open | do we need kano logo on the case?
2014-03-03 | Provide lead time of the SD card | Bob | 2014-04-03 | open
| Provide comparison between C1, C2: design, dimension, weight and cost | Bob | 2014-10-03 | open

## Management
Date | Task | Responsible | Due Date | Status | Comments
21/01/2014 | Give breakdown of the NRE | Fergal | 30/01/2014 | closed | Submit as part of Development SOW
28/01/2014 | Submit Development SOW for review | Fergal | 30/01/2014 | closed
2014-10-02 | Finalise SOW for sigantures | Yonatan/Fergal | 14/02/2014 | open
28/01/2014 | Submit MSA for review | Elaine | 30/01/2014 | closed | For review and agreement ASAP
28/01/2014 | Determine Payment terms | Fergal | 21/02/2014 | open | The payment terms and other T&Cs are TBD as part of the MSA discussion, but as an indicator, PCH offer is typically 30days NET on FOB HK shipments.
21/01/2014 | Discuss & Review PCH fee | Fergal | 2014-06-02 | closed | Review as part of MSA and meet to discuss face to face. The Raspberry Pi & Keyboard are consigned by Kano, and the cost of management needs to reflect this. These items need to be $0 in the PCH BOM.
28/01/2014 | What is the agreement on payment for NRE | Fergal, Elaine & Yonatan | 24/02/2014 | open | Equity agreement to be discussed
21/01/2014 | What are the delivery terms | Fergal | 28/01/2014 | closed | Initial BOMs are quoted FOB HK Ocean, but can review shipment terms in MSA and future pricing agreements
28/01/2014 | Define a workable distribution model for Kano | Tom & Clare | 21/02/2014 | open | Define a solution that fits Kano's requirements.
2014-10-02 | Full production plan + milestones & lead times for shipping 1000 units to Early Bird customers by June 20th | ??? | 28/02/2014 | open
21/01/2014 | Remove Cable from BOM | Darragh | 14/02/2014 | closed | Remove from price break quotes
2014-10-02 | Full production plan + milestones & lead times for shipping 15,000 units to Early Bird customers by July 18th | ??? | 2014-12-03 | open
2014-10-02 | Fulfilment plan and finalisation of countries + proper tax planning | Yonatan/Dan | 15/03/2014 | open
2014-10-02 | Receive samples for all components as per open issues | Bob Shi | 21/02/2014 | closed | Sent all samples to Kano
2014-10-02 | Compliance/conformance markings (RoHS, CE, WEEE, FCC) on the outer sleeve packaging, Tech Specs and Health & Safety Information (of Wifi dongle, Keyboard, Raspberry Pi, Power supply) in different languages (Eng, German, French etc,?) Warranty to think about? | CP Lau/Justine | 28/02/2014 | open | Working on this issue
29/01/2014 | Send PCH factory address | Fergal | 30/01/2014 | Closed
2014-10-02 | Finalise MSA for signatures | Yonatan/Fergal | 14/02/2014 | open
21/01/2014 | Get Price break of kit | Darragh | 14/02/2014 | open | Price breaks of 15k, 20k, 50k & 100k. Wait for factories to open after CNY
21/01/2014 | Detail LT on quoted CBOM, so that we can establish inventory priority & exposure value | Bob Shi | 28/02/2014 | open

## Raspberry Pi
Task | Responsible | Due Date | Status | Comments
Confirm Shipping details- finalise cost of SHIPPING (UK --> HK) | JINGJING |  | Open
5 Raspberry Pis - delivery status? (Yon cash ready for Bob) | Yonatan | 2014-02-28 | closed
Get the final quote from Keith (Farnell) | Yonatan | 2014-02-14 | closed
Finalise quantity in June/July | Yonatan | 2014-07-03 | open
Finalise payment terms for 45 days + sign agreement | Yonatan | 2014-07-03 | open
Delivery Terms: Determine costs and logistics of movement to PCH factory | Yonatan | 2014-07-03 | open
Develop the RPi production plans for post Summer time - explore with PCH and RS | Yonatan |  | open
Include Warranty Information, Health and Safety, Tech Specs and Compliance information - discuss with FARNELL | JingJing | 14/3/14 | open
Add cost of Rpi - to BOM | JingJing | 28/2/14 | open

## Keyboard
Task | Responsible | Deadline | Status | Comment
Riitek to confirm name of plastic | Jingjing | 14/02/2014 | closed | yes
Riitek to test new PCB: RF and Bluetooth | Lisa | 14/03/2014 | open
Confirm that the quotes include a red cable | Jingjing | 14/02/2014 | closed | yes
Confirm numbers and packaging for shipment to PCH | JingJing | 28/03/2014 | open
Riitek - hand sample ready by Yon's China visit | JingJing | 2014-08-03 | open
Confirm posession of domestic license | Jingjing | 14/02/2014 | closed | they have business license and tax registration certificate
Confirm performance specifications regarding keyboard with Riitek | Jingjing | 2014-07-03 | open
Riitek to confirm technical specifications to go on the back of the keyboard (e.g. voltage and current requirements and specs) | Jingjing | 28/02/2014 | closed
Make sure that the relevant conformance symbols to go on the back of the keyboard (e.g. WEEE, RoHS, CE recycling) | Jingjing | 28/02/2014 | open | MAKE SURE the right symbols will go on each kayboard | Riitek only does FCC ,CE,Rosh
Charging cable – USB symbol on both sides of the red charging cable. | Jingjing | 28/02/2014 | open
Warranty information and instruction card (regarding bluetooth and RF)- confirm with Riitek | Jingjing | 28/02/2014 | open | SEPARATE SKU
Decide on KANO logo layout for the Keyboard? |  | 28/02/2014 | closed
Find out if it is useful to get Utility Design for Keyboard and RasPi Case | Yonatan |  | open | Designed specially for young people
|  |  | open | Two handed - two key plus touch pad to navigate
Get lead time for the PCB | Jingjing |  | open | PCBA is finished, waiting to update software
Confirm with Lisa the hand sample | Jingjing | 2014-08-03 | open | Should finish on time
Need to verify with Lisa and Bob about the red cable | Jingjing | 27/02/2014 | closed | Riitek is going to make the red use cable
Send full specification of the keyboard to Kano | Jingjing | 2014-07-03 | closed | Lisa will finish the translation on 3/3/14
Design a instruction card for the keyboard with Mathew + Tommy | Jingjing | 2014-07-03 | open | PCH should produce them
deliver to PCH at least 2 weeks before 20/06

## Books
| Task | Responsible | Deadline | Status | Comment
Book 1 2/11/2014 |  | Lilian | 2014-02-28 | open
| 24 pp (confirm it is same materialand gsm as lego sample) | Lilian/Jingjing | 2014-02-18 | closed | sample sent
| PCH to provide sample to confirm: | Lilian/Jingjing | 2014-02-18 | closed | material and gsm same as Lego sample
| i. appearance | Lilian/Jingjing | 2014-02-18 | closed
| ii. material | Lilian/Jingjing | 2014-02-18 | closed
| iii. artwork | Lilian/Jingjing | 2014-02-18 | open
| Send artwork to PCH | Jingjing | 2014-02-12 | open
Book 2 2/11/2014 |  | Lilian | 2014-02-28 | open | sample sent
| 72 pp (confirm it is same materialand gsm as lego sample) | Lilian/Jingjing | 2014-02-18 | open | material and gsm same as Lego sample
| PCH to provide sample to confirm: | Lilian/Jingjing | 2014-02-18 | closed
| i. appearance | Lilian/Jingjing | 2014-02-18 | open
| ii. material | Lilian/Jingjing | 2014-02-18 | open
| iii. artwork | Lilian/Jingjing | 2014-02-18 | open
| Send artwork to PCH | Jingjing | 2014-02-12 | open
Book 3 |  | Lilian | 2014-02-28 | open
| 72 pp (confirm it is same materialand gsm as lego sample) | Lilian/Jingjing | 2014-02-18 | open
| PCH to provide sample to confirm: | Lilian/Jingjing | 2014-02-18 | open
| i. appearance | Lilian/Jingjing | 2014-02-18 | open
| ii. material | Lilian/Jingjing | 2014-02-18 | open
| iii. artwork | Lilian/Jingjing | 2014-02-18 | open
| Send artwork to PCH | Jingjing | 2014-02-12 | open
| Folder to keep the books |  |  | open
27/02/2014 | get sample with light blue background for both books same thickness | Jingjing |  | open | artwork sent
27/02/2014 | sample with 90gsm white background | Jingjing |  | open | artwork sent
27/02/2014 | UPDATE ARTWORK | Jingjing |  | open | artwork sent
27/02/2014 | sample 115 gsm with white background | Jingjing |  | open | artwork sent
27/02/2014 | get number of pages for the quote | Jingjing | 2014-07-03 | open | Atm 24 & 80, awaiting Tommy and Alex to decide on the new books
24/02/2014 | samples of book are not good, will check with Justine and lilian for making new sample | Lilian Zhu/Justine | 2014-10-03 | open

## Power Supply
Task | Responsible | Due Date | Status | Comments
PCH to provide sample of red power supply and all FOUR regional (UK,AUS,US,EU) adapters for: | Lilian/Jingjing | 18/02/2014 | closed | sample sent
i. Testing | Lilian/Jingjing | 18/02/2014 | open
ii. Confirm appearance | Lilian/Jingjing | 18/02/2014 | open
Confirm colour (see descriptions doc) | Lilian/Jingjing | 24/02/2014 | open
Confirm that judoka's chin is facing towards USB port | Lilian/Jingjing | 24/02/2014 | open
Get new quotes from Stontronics for the power supply and then connect them to Bob for coordination | Jingjing/Yonatan | 28/02/2014 | open
Testing the power plug | Senthil | 28/02/2014 | open
Check if the prototypes with include Kano logo | Jingjing |  | open

## Packaging
| Task | Responsible | Due Date | Status | Comments
ALL | Do a quick drawing of the new packaging design. | Scott |  | open
Inner Box |  | Josa | 2014-04-05 | open
| New options for materials + production, and quoting from Josa | Josa | 2014-02-21 | open
| PCH to confirm material after choosing final material | Josa | 2014-02-24 | open
| Discuss with MAP and confirm making samples | Josa | 2014-02-25 | open
| PCH to provide samples | Josa | 2014-03-15 | open
| Confirm final production details | Josa | 2014-03-25 | open
|  |  |  | open | Packaging development has not started yet, since the NRE cost not confirmed
Tyvek Envelope |  | Josa | 2014-02-28 | open
| PCH to prepare more alternative samples: something more protective – ORANGE jiffy bag envelope, more envelope options | Josa | 2014-02-21 | open | Lilian - looking for jiffy bags - easy and good protection, finding samples and supported by data. Pay for sample fee to make custom colours
| Test suitability for global shipping | Josa | 2014-02-28 | open
| PCH to provide quotes for alternative options | Josa | 2014-02-28 | open
open
Outer Sleeve |  | Josa | 2014-04-05 | open
| New options for materials + production, and quoting from Josa | Josa | 2/242014 | open
| Discuss with MAP and confirm making samples | Josa | 2014-02-28 | open
| PCH to provide samples | Josa | 2014-03-15 | open
| Confirm final production details | Josa | 2014-03-25 | open
|  |  |  | open | PCH has final PP layer that is anti scratch
Envelope for book |  | Josa | 2014-04-05 | open
| New options for materials + production, and quoting from Josa | Josa | 2014-02-24 | open
| Discuss with MAP and confirm making samples | Josa | 2014-02-28 | open
| PCH to provide samples | Josa | 2014-03-15 | open
| Confirm final production details | Josa | 2014-03-25 | open
| Find possible graphics of the envelope | Tommy/MAP | 28/02/2014 | open
| Find a thin and strong folder for the books. | Josa/MAP/Yonatan | 28/02/2014 | open
open
Plastic Tray |  | Josa | 2014-04-05 | open
| New options for materials + production, and quoting from Josa | Josa | 2014-02-24 | open
| Discuss with MAP and confirm making samples | Josa | 2014-02-28 | open
| PCH to provide samples | Josa | 2014-03-15 | open
| Confirm final production details | Josa | 2014-03-25 | open
| New design |  | 2014-05-03 | open
21/02/2014 | Packaging concept design to be done | Josa Leung | 28/02/2014 | open
24/02/2014 MAP Meeting Notes
Envelope - bigger size to accommodate 3 books ( 70, 70 & 20), stickers and cards, current design - imbalance due to weight of the books. position move to the middle. Using an orange plastic material, folder like. | Box - Delete the window, put the books side by side | Tooling - changing every 1000 instead of 500 if using a rectangular cutting
REARRANGE positioning of all the components: | move the power plugs to the top, on the right side of the keyboards. Rotating the hole for the case 180 degrees, speaker will sit on top of the case, and case card lys underneath, shift to the left side. Case can be pre-assembled with the speaker, users need to de-assemble the case and put the Pi in. | SD card and wifi dongle will be placed at the centre of the bottom space. | The case cards will go underneath the RasPi Case
On the Case Card - Engrave “my Kano” on the top of the Card, leave blank space under so Children can put stickers in the space.
Make sure everything is tightened/lock in.
21/02/2014 PCH Meeting Notes
Josa kicked off the packaging development since last week, she would send the material proposition to you by middle of next week. | ENVELOPE: custom made of the envelope with nice appeal. jeffy bag in samples from suppliers. has the relevant protection. OUTER SLEEVE: they found anti-scratch. sending samples. THE BOX: 3 directions: 1) continuing the existing direction - stronger structure. 2) craft-looking paper. 3) Xiaomi-like sample. VAC FORM: we are fine with the vac form as the tray solution and we need to find a solution for the speaker units. ENVELOPE: we need to redesign the location, size and material of the envelope | Tue/Wed next week | we have a problem with the window. do we want a cut out in the inner box or just have a rectangular cut out. | Envelop, a bit of deform, going to have a tighter opening which is from the top. Using matt material, black scratch will be hard to notice.

## Speaker
Date | Task | Responsible | Due Date | Status | Comments
2014-02-25 | Finalise the size of the speaker | Senthil |  | open
2014-02-25 | Solve the off centre problem with the speaker within 2 days. | Bob | 27/02/2014 | open
2014-02-25 | Test this problem with speaker case vibration as RasPi is not very powerful. | Senthil |  | open
2014-02-24 | Create the final prototype and start tooling. |  | 2014-03-05 | open
2014-02-24 | Need to verify how PCH is going to do glue the speaker |  |  | open
2014-02-24 | Get different Electrical certification needed for different geographic locations. |  |  | open
2014-02-24 | Explore heat sink options | Senthil, JingJing & Jingjing |  | open
2014-02-24 | Tested with amplifier, too powerful that vibrates intensely, need to Reduce the power? |  |  | open
2014-02-24 | New design 10mm thick, need to make sure it fits in the box. |  |  | open
2014-02-24 | a. PCB, speaker unit, GPIO, speaker plastic – finalise sample & quotes. | Mick/Senthill | 2014-02-18 | open | Mick is working on the PCBA that Senthil send us a link
2014-02-24 | b. PCH initial components to test suitability for working with the Rpi | Mick/Senthill | 2014-02-18 | open
2014-02-24 | PCH to confirm production availability | Mick/Senthill | 2014-02-24 | open
2014-02-24 | PCH to provide quote per unit & tooling lead time and costs | Mick/Senthill | 2014-02-24 | open
2014-02-24 | Make final prototype + confirm model for production | Mick/Senthill | 2014-02-28 | open
2014-02-24 | SLA samples available for checking | Jacky | 2014-03-05 | open | Preparing 3D printed sample, will be avialbe by next Tuesday
2014-02-24 | After confirming electronics, finalise plastic with MAP | Mick/Jacky/MAP | 2014-02-28 | open
2014-02-24 | PCH to provide sample for apperance and testing | Mick/Senthill | 2014-02-28 | open
2014-02-24 | PCH to provide quote per unit & tooling lead time and costs | Mick/Senthill | 2014-02-24 | open
2014-02-24 | PCH and Kano to confirm model for production | Mick/Senthill | 2014-02-28 | open
2014-02-24 | Determine deadline to start tooling to ship 1k units by 20/06/2014 | Mick/Senthill | 2014-02-28 | open
21/02/2014 | New Speaker and PCBA samples are ready for testing | Eddie/Mick Foo | 28/02/2014 | Open
21/02/2014 | 60 speakers samples | Mick Foo | 2014-07-03 | open
21/02/2014 PCH Meeting Notes
| 1. I will send the Pro-E file to Scott for reference for the assembly of speaker. Mick said he would keep looking for the low height speaker that would fix this cover higher than case problem. |  | Bob - next tuesday to get back to us on a smaller PCBA. Speaker size - bigger issue - Bob to investigate to find a smaller size speaker
2. Eddie and Andrew they are doing the testing today and will take vedio for reference. I will send to you late.
3. I will ask for the testing data from Eddie and send to Senthil
4. As I talked to Mick this afternoon, he said we already found out the supplier for PCBA, it was small size, and we could modify it a little bit to fit to our the product requirements.
5. Mick prefered Senthil to make the prototype sample in UK and send design to us, we then can replication and send to our supplier for manufacturing.
6. As Mick proposed, we would like to fix the Speaker and Speaker little PCBA onto the speaker cover. I will ask Andrew to find a design solution, then send to Scott for confirmation.
Speaker Mick already got the samples, Speaker and PCBA, his team is testing them today. Will let you know the results.
| The 3D printed sample was done yesterday, we are doing the testing in the lab today. I would send some video to you for reference late today. 1. Testing from the sample, there is slightly interference on the masts when clipped together. I will send to samples to you for reference. 2. Andrew said we could beef up the clip a little bit if you need. We will let you check the prototype sample first. |  | 2 days to make a sample
| Case + Speaker cover: Design modifications, will send out PPT file late in another e-mail | Scott received the DFM and will discuss with Jacky. main open issues: 1. clipping mechanism / 2. 3D not matched
| Speaker and little PCBA discussion | Open issues: sample sent to Senthill. the problem is that the speaker unit is too big + there's a vibration problem | speaker sample arrives on Monday + answer on PCB on Tuesday. Bob’s team will receive a smaller PCB next Tuesday. | Turn the speaker cover inside down? Change the shape of the cover so the speaker is sticking out.

## SD Card
Date | Task | Responsible | Due Date | Status | Comments
| a. Need to change logo : | Lilian/Jingjing | 2014-02-18 | open | Need to have software to make samples | software provided
| i. 8GB sign on the corner | Lilian/Jingjing | 2014-02-18 | open
| ii. Middle: Judoka face Bottom: New kano logo with pins | Lilian/Jingjing | 2014-02-18 | open
| iii. Other specifications at back of SD Card(e.g. class 10, CE/FCC conformance, Country of Manufacture) | Lilian/Jingjing | 2014-02-18 | open
| b. PCH to provide sample with the Kano OS pre-loaded + new artwork | Lilian | 2014-02-18 | open
| Test samples of SD card of different speed |  |  | open
28/01/2014 | Add SD card to BOM quote | Bob SHi | 28/02/2014 | open | Add to price break quotes. Screen printed with OS loaded - 8GB
29/01/2014 | What are the delivery terms for the Raspberry & Keyboard - FOB HK or DDU PCH Factory. | Justine | 24/02/2014 | open | What licenses do the 2 factories have - export or domestic?
29/01/2014 | Provide a specification of each component that is sourced by PCH | Bob Shi | 21/03/2014 | open
21/02/2014 | DFM for mechanical parts need to be reviewed and finalized | Andrew Liu/Scott | 28/02/2014 | Open
21/02/2014 | SD card sample availability | Lilian Zhu | 2014-03-03 | open
21/02/2014 | SD card sample will send to Kano | Lilian Zhu | 2014-05-03 | open

## Red USB Cable
| Task | Responsible | Due Date | Status | Comments
| PCH to provide sample of red cable: | Lilian/Jingjing | 18/02/2014 | closed | sample sent
| i. Testing | Lilian/Jingjing | 18/02/2014 | open
| ii. Confirm appearance | Lilian/Jingjing | 20/02/2014 | open | We can send some samples to yo for reference first
| Explore extra costings and processing time of judoka face on end | Lilian/Jingjing | 18/02/2014 | open
| PCH to confirm coating material and end plastic | Lilian | 24/02/2014 | closed | There is no coating, the plastic is PVC
| test for durability | Jingjing |  | open
21/02/2014 | 60 USB cable samples | Lilian Zhu | 407065 | open

## HDMI Cable
| Task | Responsible | Due Date | Status | Comments
| PCH to provide option and sample for a less stiff, more flexible & flat (Just like the red USB/MicroUSB cable) | Lilian | 18/02/2014 | closed
| b. Possibility of Kano face (cost and screen print process and tooling) | Lilian/Jingjing | 18/02/2014 | open
| c.PCH to provide sample of HDMI cable: | Lilian/Jingjing | 18/02/2014 | closed | sample sent
| i. Testing | Lilian/Jingjing | 18/02/2014 | open
| ii. Confirm appearance | Lilian/Jingjing | 18/02/2014 | open
| Explore extra costings and processing time of judoka face on end | Lilian | 24/02/2014 | open
| PCH to confirm coating material and end plastic | Lilian | 28/02/2014 | open
Comfirm the quotes for the cable
test for durability
21/02/2014 | 60 yellow HDMI cable samples | Lilian Zhu | 407065 | open

## Stickers
Task | Responsible | Due Date | Status | Comments
PCH to provide sample to confirm: | Lilian/Jingjing | 18/02/2014 | open | Blank sample available to check the material | Blank Sample has arrived
i. appearance | Lilian/Jingjing | 18/02/2014 | open
ii. material | Lilian/Jingjing | 18/02/2014 | open
iii. artwork | Lilian/Jingjing | 18/02/2014 | open

## Wifi Dongle
Task | Responsible | Due Date | Status | Comments
PCH to confirm plastic material and that it will be totally green | Lilian | 18/02/2014 | closed | awaiting black sample
Explore extra costings and processing time of judoka face on the end | Lilian/Jingjing/Yon | 24/02/2014 | open
a. Get sample for: | Lilian/Jingjing | 18/02/2014 | closed | verify the specs
i. Testing, and ensuring compliant with Raspberry Pi | Lilian/Jingjing | 18/02/2014 | open
ii. Confirm appearance | Lilian/Jingjing | 24/02/2014 | open
Confirm Wifi dongle specs (see descriptions doc) | Lilian | 18/02/2014 | open

## Clear Case Box
Task | Responsible | Due Date | Status | Comments
(2 pieces and 1 cover) | Jacky | 2014-03-05 | open | 3D printed sample is available
Finalise the case engineering with Jacky's team from Shenzhen: | Jacky | 2014-02-28 | open
Finalise engineering and design changes | Jacky | 2014-02-18 | open
make final prototype | Jacky | 2014-02-24 | open
confirm final model for production | Jacky | 2014-02-28 | open
Check if ‘Made in China’ needed for the case? | JingJing/Jingjing |  | open
On the Case Card - Engrave “my Kano” on the top of the Card, leave blank space under so Children can put stickers in the space. |  |  | open

## Inner Case Cards
Task | Responsible | Due Date | Status | Comments
4 case cards; blue, yellow, green, red | Lilian/Jingjing | 2014-02-28 | open
PCH to provide sample to confirm: | Lilian/Jingjing | 2014-02-18 | closed | sample available
i. appearance | Lilian/Jingjing | 2014-02-18 | open
ii. material | Lilian/Jingjing | 2014-02-18 | open
iii. artwork | Lilian/Jingjing | 2014-02-18 | open
Need to be thicker and with my kano in small writing on the centre on the top of the card | jingjing |  | open | work with Tommy

## COMPLIANCE
Task | Responsible | Due Date | Status | Comments
Confirm with Yonatan regarding TUV classification of toy product | CP, JINGJING | asap | open
Discuss KC classification with Lisa - requirements for other countries | JingJing |  | open

## 21.02.2014
21st February Conference Call
PCBA shipping term discussion
Samples send to Jingjing today. | done - Monday EOD
Case + Speaker cover: Design modifications, will send out PPT file late in another e-mail | Scott received the DFM and will discuss with Jacky. main open issues: 1. clipping mechanism / 2. 3D not matched
Testing results sharing | done
Speaker and little PCBA discussion | Open issues: sample sent to Senthill. the problem is that the speaker unit is too big + there's a vibration problem | speaker sample arrives on Monday + answer on PCB on Tuesday
Overall review and discussion
Packaging Josa kicked off the packaging development since last week, she would send the material proposition to you by middle of next week. | ENVELOPE: custom made of the envelope with nice appeal. jeffy bag in samples from suppliers. has the relevant protection. OUTER SLEEVE: they found anti-scratch. sending samples. THE BOX: 3 directions: 1) continuing the existing direction - stronger structure. 2) craft-looking paper. 3) Xiaomi-like sample. VAC FORM: we are fine with the vac form as the tray solution and we need to find a solution for the speaker units. ENVELOPE: we need to redesign the location, size and material of the envelope | Tue/Wed next week | we have a problem with the window. do we want a cut out in the inner box or just have a rectangular cut out.
Speaker Mick already got the samples, Speaker and PCBA, his team is testing them today. Will let you know the results.
The 3D printed sample was done yesterday, we are doing the testing in the lab today. I would send some vedio to you for reference late today. 1. Testing from the sample, there is slightly interference on the masts when clipped together. I will send to samples to you for reference. 2. Andrew said we could beef up the clip a little bit if you need. We will let you check the prototype sample first. |  | 2 days to make a sample
Power supply | get new quotes from Stontronics for the power supply and then connect them to Bob for coordination